Work Breakdown Structure

Community Lost & Found Matching Network — Problem Statement #59

Author: Swaroop Venkateshwar (PES1UG24CS923)

Course: Software Engineering, Dept. of CSE, PES University

Planning tool: Jira Scrum project Scrum_BPS#59 (key SBPS59) and a Kanban project, Kanban_BPS#59

# 1. Approach

The project is broken into six phases, and each phase into work packages. Implementation work is organised by user story and follows the Jira Scrum project: one epic, Epic 1: Lost & Found Item Matching (SBPS59-8), with seven tasks that mirror the requirements (SBPS59-1 to SBPS59-7) and seven user stories (SBPS59-9 to SBPS59-15) carrying 47 story points in total.

Story points use the Fibonacci scale. A story’s size reflects how much work and risk it carries, which is why the performance story is the largest at 13 points.

# 2. Work Breakdown

| WBS ID | Work package | Deliverable | Jira / source |
| --- | --- | --- | --- |
| 1 | Requirements Engineering |  |  |
| 1.1 | Analyse problem statement, identify actors | Actors: Finder / Owner, Community Admin | Lab 1 |
| 1.2 | Write functional and non-functional requirements | FR-001 to FR-005, NFR-001, NFR-002 | Lab 1 |
| 1.3 | Model use cases | Use-case diagram (7 use cases), UC-04 flow specification | Lab 1 |
| 1.4 | Specify alternate and exception flows | Alternate flows, EX-001 to EX-004 | Lab 1 |
| 1.5 | Build the traceability matrix and test cases | RTM, TC-001 to TC-019 | RE document |
| 2 | Project Setup and Planning |  |  |
| 2.1 | Create the GitHub repository | Repository with README and numbered folders | GitHub |
| 2.2 | Set up the Jira Scrum project | Epic 1, 7 tasks, 7 stories with story points, 2 sprints | SBPS59-1 to -15 |
| 2.3 | Set up the Jira Kanban project | Kanban board with the same epic, tasks and stories | Kanban_BPS#59 |
| 3 | Specification and Design |  |  |
| 3.1 | Write the SRS | IEEE 830-style SRS | SRS document |
| 3.2 | Design the architecture | Architecture diagram and component description | Architecture document |
| 3.3 | Design the data model | Logical data model (SRS section 3.7) | SRS document |
| 4 | Implementation (one work package per user story) |  | Epic SBPS59-8 |
| 4.1 | Post Found Item: found-item form with photo and location, validation, saving | FR-002 working end to end | SBPS59-10, 5 pts |
| 4.2 | Post Lost Item: lost-report form with search radius, validation, saving | FR-003 working end to end | SBPS59-11, 5 pts |
| 4.3 | Item Matching: match by category, colour tags and location radius, with match probability | FR-001 working end to end | SBPS59-9, 8 pts |
| 4.4 | Match Notifications: push and email to Finder and Owner | FR-004 working end to end | SBPS59-12, 3 pts |
| 4.5 | Admin Moderation: review, flag and remove posts, with audit log | FR-005 working end to end | SBPS59-13, 5 pts |
| 4.6 | Ownership Verification: security questions, 3 attempts, 24-hour lock, contact reveal | NFR-001 working end to end | SBPS59-14, 8 pts |
| 4.7 | Fast Match Response: indexing and asynchronous matching so results arrive in under 3 s at 100,000 listings | NFR-002 met | SBPS59-15, 13 pts |
| 5 | Testing |  |  |
| 5.1 | Run functional tests for each story | TC-001 to TC-011 and TC-019 results | RE document |
| 5.2 | Run security tests on claim verification | TC-012 to TC-016 results | RE document |
| 5.3 | Run the performance (load) test | TC-017 result at 100,000 listings | SBPS59-22 (sub-task of SBPS59-6) |
| 5.4 | Test failure handling | TC-018 (matching service down), TC-005 (duplicate post) | RE document |
| 6 | Documentation and Delivery |  |  |
| 6.1 | Write the repository README | README linking every folder | GitHub |
| 6.2 | Capture GitHub Copilot code evidence | Screenshots or repository link | GitHub |
| 6.3 | Submit the repository | Final repository link | GitHub |

Top-level phases (1 to 6) are summary rows; the work packages beneath them carry the deliverables.

# 3. Sprint Plan

Work was run as a Scrum project in Jira with two sprints on the epic.

## 3.1 Sprint 1

Sprint 1 was started with four stories in To Do, 21 story points in total, and moved across the board columns (To Do, In Progress, In Review, Done) as the work progressed.

| Story | Title | Requirement | Points |
| --- | --- | --- | --- |
| SBPS59-9 | Item Matching | FR-001 | 8 |
| SBPS59-10 | Post Found Item | FR-002 | 5 |
| SBPS59-11 | Post Lost Item | FR-003 | 5 |
| SBPS59-12 | Match Notifications | FR-004 | 3 |
|  | Total |  | 21 |

## 3.2 Sprint 2

Sprint 2 ran from 30 August to 6 September 2026. It picked up three of the Sprint 1 stories, together with the task for FR-001, and started with 16 story points. Jira recorded no scope changes during the sprint.

| Item | Title | Requirement | Points |
| --- | --- | --- | --- |
| SBPS59-9 | Story: Item Matching | FR-001 | 8 |
| SBPS59-11 | Story: Post Lost Item | FR-003 | 5 |
| SBPS59-12 | Story: Match Notifications | FR-004 | 3 |
| SBPS59-1 | Task: FR-001 Match Found & Lost items | FR-001 | — |
|  | Total at sprint start |  | 16 |

The Sprint 2 burndown chart, with story points as the estimation field, and the sprint report are included in the Jira screenshots in the repository.

## 3.3 Stories not yet scheduled

Three stories were not placed in either sprint and remain in the backlog.

| Story | Title | Requirement | Points |
| --- | --- | --- | --- |
| SBPS59-13 | Admin Moderation | FR-005 | 5 |
| SBPS59-14 | Ownership Verification | NFR-001 | 8 |
| SBPS59-15 | Fast Match Response | NFR-002 | 13 |
|  | Total of these three stories |  | 26 |

Together with the 21 points in section 3.1, the epic totals 47 story points.

# 4. Dependencies Between Work Packages

| Work package | Depends on | Reason |
| --- | --- | --- |
| 4.3 Item Matching | 4.1, 4.2 | Matching needs both found posts and lost reports to exist. |
| 4.4 Match Notifications | 4.3 | A notification is sent only when a match has been identified. |
| 4.6 Ownership Verification | 4.3, 4.4 | A claim starts from a match the Owner was notified about. |
| 4.5 Admin Moderation | 4.1, 4.2 | Moderation acts on posts and reports that already exist. |
| 4.7 Fast Match Response | 4.3 | Performance tuning needs a working matching engine to measure. |
| 5 Testing | 4.x | Each test group runs once its story is built. |